## Risk Register
SAMPLE RISK REGISTER
Description | Probability | Impact | Probability | Impact | Score | Response type | Action plan | Timing | Probability | Impact | Factor
Cash flow | H | H | 3 | 3 | 9 | Mitigate | Extend credit, build balance, invoice promptly, stagger orders | Now | 0.8 | 0.8 | 0.64
Problems with cable | M | H | 2 | 3 | 6 | Avoid | Cable NIC, will test as QC process | NIC completed. Testing at delivery | 0.35 | 0.8 | 0.28
Owner reluctant to accept due of integrated areas do to other trades | M | H | 2 | 3 | 6 | Avoid | Establish acceptance criteria | January-March 2015 | 0.35 | 0.8 | 0.28
Schedule sequencing (compressed schedule) | M | H | 2 | 3 | 6 | Avoid | Change sequence to accommodate | November 2014 | 0.35 | 0.8 | 0.28
Schedule delays, idle resources | H | M | 3 | 2 | 6 | Mitigate | Work down back log, offer discounts, send to training, | At delay | 0.8 | 0.35 | 0.28
Issues with doors | H | M | 3 | 2 | 6 | Transfer | Accept no responsibility | Now | 0.8 | 0.35 | 0.28
Owner changes scope (change in reader/badge tech) | H | M | 3 | 2 | 6 | Mitigate | Obtain C/O and schedule extension | At change | 0.8 | 0.35 | 0.28
REX choice | H | M | 3 | 2 | 6 | Transfer | Accept no responsibility | December 2014 | 0.8 | 0.35 | 0.28
Gates, barrier arms, and roll up safety devices | H | M | 3 | 2 | 6 | Transfer | Accept no responsibility | December 2014 | 0.8 | 0.35 | 0.28
Delays in Owner provided switches | M | M | 2 | 2 | 4 | Mitigate | Obtain schedule extension | At delay | 0.35 | 0.35 | 0.1225
Lack of owner resources | M | M | 2 | 2 | 4 | Mitigate | Obtain schedule extension | At delay | 0.35 | 0.35 | 0.1225
Damage to finishes | M | M | 2 | 2 | 4 | Accept | Repair damage at our cost | At last possible moment | 0.35 | 0.35 | 0.1225
Site access, lifts | M | M | 2 | 2 | 4 | Mitigate | Stage for next day at day close | Every day | 0.35 | 0.35 | 0.1225
Price increases from factory | M | M | 2 | 2 | 4 | Accept | Reduce GM | After purchased | 0.35 | 0.35 | 0.1225
Shipping cost increases (fuel costs) | M | M | 2 | 2 | 4 | Accept | Reduce GM | After delivery | 0.35 | 0.35 | 0.1225
Faulty design from F+P | H | L | 3 | 1 | 3 | Accept | Correct at our cost | When discovered | 0.8 | 0.1 | 0.08
Lack of resources | L | H | 1 | 3 | 3 | Accept | Contract qualified LSP | Identify LSP in planning stage, engage 6 weeks before shortage | 0.1 | 0.8 | 0.08
Unable to configure switches, network issues | L | H | 1 | 3 | 3 | Accept | Hire contract engineer to configure | Identify engineer in planning phase, engage 4 weeks before Owners acceptance | 0.1 | 0.8 | 0.08
Batteries | L | H | 1 | 3 | 3 | Avoid | Connect PSU to UPS | December 2014 | 0.1 | 0.8 | 0.08
Field modifying door parts | L | H | 1 | 3 | 3 | Mitigate | Obtain C/O and schedule extension | February 2015 | 0.1 | 0.8 | 0.08
Noise on cameras | L | H | 1 | 3 | 3 | Transfer | Accept no responsibility |  | 0.1 | 0.8 | 0.08
HID readers not working | L | H | 1 | 3 | 3 | Accept | Re-sequence or crash schedule | After prototype phase | 0.1 | 0.8 | 0.08
Pro serv staff turnover | L | H | 1 | 3 | 3 | Mitigate | Establish back-up resource | December 2014 | 0.1 | 0.8 | 0.08
Liquidated damages | L | H | 1 | 3 | 3 | Avoid | Document all delays | 5 day turnaround after delay identified | 0.1 | 0.8 | 0.08
Theft | M | L | 2 | 1 | 2 | Accept | Re-purchase | Most material not stored on site | 0.35 | 0.1 | 0.035
Factory delivery delays | L | M | 1 | 2 | 2 | Accept | Re-sequence or crash schedule |  | 0.1 | 0.35 | 0.035
High failure rate from fabricating | L | M | 1 | 2 | 2 | Transfer | Reject product |  | 0.1 | 0.35 | 0.035
Labor turnover | L | M | 1 | 2 | 2 | Accept | Backfill |  | 0.1 | 0.35 | 0.035
Errors and omissions in design and estimate | L | L | 1 | 1 | 1 | Accept | Correct at our cost |  | 0.1 | 0.1 | 0.01
ADA doors integration | L | L | 1 | 1 | 1 | Transfer | Accept no responsibility |  | 0.1 | 0.1 | 0.01
1. Avoidance: change a risky method, technique, technology, or remove items from scope.
2. Transference: place risk somewhere else, for example in insurance or with another contractor. Document changes, delays, etc. to place risk on another
3. Mitigate: alternate schedule, contingency plan
4. Acceptance: a cost over-run or schedule slip

## Risk Scoring
Risk Scoring Matrix
Impact | Critical | 3 | 3 | 6 | 9
| Serious | 2 | 2 | 4 | 6
| Marginal | 1 | 1 | 2 | 3
|  |  | 1 | 2 | 3
|  |  | Less likely | Likely | Certain
Probability
Risk Category & Action
Key/ Critical Risks - closely monitor, manage & develop fallback plans
Intermediate Risks - monitor and manage to mitigate/ include specific risk allowances in cost estimate/ programme
Minor Risks - general allowance in base cost estimate & programme
Probability Categories
Description |  | Prob | Scale Value
H | Probable | >70% | 3
M | Could happen | 30-70% | 2
L | Improbable | <30% | 1
Impact Categories
Description |  | Guide Scenario |  |  |  | Scale Value
H | Critical | Failure that involves significant rework, modification or reassessment |  |  |  | 3
M | Serious | Failure or setback that causes additional work and reassessment but containable |  |  |  | 2
L | Marginal | Impact has some effect causing rework or reassessment but easily handled |  |  |  | 1